## Sprint Tasks
Task ID | Sprint | Month | Role | Workstream | Task | Deliverable | Priority | Planned Start | Planned End | Owner | Status | % Complete | Weight | KPI Link | OKR Link | Dependencies | Evidence Link | Risk Level | RAG | Notes
| 1 | July | BE | Auth | Setup Redis Service | Redis connections wrapper module | HIGH | 2026-07-06 | 2026-07-07 | superadmin@indotek.com | DONE | 1 | 1 |  |  |  |  | LOW | GREEN | Zero dependency wrapper
| 1 | July | BE | Auth | Prisma Audit Log middleware | Prisma Client write logger | HIGH | 2026-07-06 | 2026-07-08 | superadmin@indotek.com | DONE | 1 | 1.5 |  |  |  |  | LOW | GREEN | Logs actor and state
| 1 | July | BE | API | Create Project CRUD endpoints | Project routes and services | MEDIUM | 2026-07-07 | 2026-07-09 | superadmin@indotek.com | DONE | 1 | 1 |  |  |  |  | LOW | GREEN | PM_ADMIN restricted
| 1 | July | BE | API | Create Sprint CRUD with overlap check | Sprint routes with validations | HIGH | 2026-07-07 | 2026-07-10 | superadmin@indotek.com | IN_PROGRESS | 0.8 | 1.5 |  |  |  |  | MEDIUM | GREEN | Throws SPRINT_OVERLAP on collision
| 1 | July | BE | API | Task CRUD and generator logic | Task code formatter helper | MEDIUM | 2026-07-08 | 2026-07-10 | superadmin@indotek.com | IN_PROGRESS | 0.7 | 2 |  |  |  |  | LOW | GREEN | Code prefix formatting SS-NNNN
| 1 | July | BE | Import | Excel Import Preview Endpoint | Tasks preview route | HIGH | 2026-07-08 | 2026-07-11 | TBD | IN_PROGRESS | 0.5 | 1.5 |  |  |  |  | LOW | GREEN | Checks dates within sprint boundaries
| 1 | July | BE | Import | Excel Import Commit Endpoint | Transaction batch save tasks | HIGH | 2026-07-09 | 2026-07-11 | TBD | NOT_STARTED | 0 | 1.5 |  |  |  |  | LOW | GREEN | Uses Redis preview data
| 1 | July | FE | Web UI | Project/Sprint UI manager tab | Project configuration screen | MEDIUM | 2026-07-07 | 2026-07-09 | TBD | IN_PROGRESS | 0.9 | 1 |  |  |  |  | LOW | GREEN | Tailwind style shell
| 1 | July | FE | Web UI | Task board table view | Sprint task tracker board | HIGH | 2026-07-08 | 2026-07-11 | TBD | IN_PROGRESS | 0.6 | 1.5 |  |  |  |  | LOW | GREEN | Responsive layout
| 1 | July | FE | Web UI | My Tasks board page | Task Saya mobile desktop filters | HIGH | 2026-07-09 | 2026-07-11 | TBD | NOT_STARTED | 0 | 2 |  |  |  |  | LOW | GREEN | Readonly for colleagues
| 1 | July | FE | Web UI | Bulk task Excel import drawer | Upload file overlay and review | MEDIUM | 2026-07-10 | 2026-07-12 | TBD | NOT_STARTED | 0 | 1 |  |  |  |  | LOW | GREEN | Displays error rows
| 1 | July | QA | Test | Unit test progress aggregation | Vitest test cases suite | HIGH | 2026-07-11 | 2026-07-12 | TBD | NOT_STARTED | 0 | 1 |  |  |  |  | LOW | GREEN | Verifies RAG thresholds
| 1 | July | QA | Test | Integration test sprint overlaps | Vitest spec checks overlap | MEDIUM | 2026-07-11 | 2026-07-13 | TBD | NOT_STARTED | 0 | 1 |  |  |  |  | LOW | GREEN | Blocks collision
| 1 | July | QA | Test | Manual verification of Web import | Manual import checks | MEDIUM | 2026-07-12 | 2026-07-14 | TBD | NOT_STARTED | 0 | 0.5 |  |  |  |  | LOW | GREEN | Upload excel sheet
| 1 | July | PO | Design | Define sprint targets and goal | Functional specs documentation | HIGH | 2026-07-06 | 2026-07-07 | TBD | DONE | 1 | 1 |  |  |  |  | LOW | GREEN | Approved by Indotek
| 1 | July | PO | Design | Establish Sprint RAG threshold limits | RAG rules document | MEDIUM | 2026-07-07 | 2026-07-08 | TBD | DONE | 1 | 1 |  |  |  |  | LOW | GREEN | 85/60 limits defined
| 1 | July | SA | Architecture | Design DB Task schemas | ERD task specifications | CRITICAL | 2026-07-06 | 2026-07-07 | superadmin@indotek.com | DONE | 1 | 2 |  |  |  |  | LOW | GREEN | 33 tables schema mapped
| 1 | July | SA | Architecture | Setup Redis caching strategy | Caching strategy document | HIGH | 2026-07-07 | 2026-07-08 | superadmin@indotek.com | DONE | 1 | 1 |  |  |  |  | LOW | GREEN | 1h cache expiry config
| 1 | July | Infra | DevOps | Configure Docker redis port mappings | docker-compose updates | HIGH | 2026-07-06 | 2026-07-07 | TBD | DONE | 1 | 1 |  |  |  |  | LOW | GREEN | Redis port 6379 exposed
| 1 | July | Infra | DevOps | Verify local deployment build | Production bundle build scripts | MEDIUM | 2026-07-12 | 2026-07-13 | TBD | NOT_STARTED | 0 | 1 |  |  |  |  | LOW | GREEN | Monorepo build execution